## Sheet1
GENESYS TOWER PROJECT
SL.NO. | TOWER DETAILS | RESOURCE | START DATE | TARGET DTAE | END DATE | SUBMITTED DATE TO CLIENT | 1ST COMMENTS RECEIVED DATE | SUBMITTED WITH UPDATED COMMENTS | MAN HOURS | QC HOURS | COMMENTS UPDATED HOURS | APPROVED
1 | 1302_ES-37-083450_RT_VITIGUDINO SAN ROQUE 11 ATW_83650 | RAJ SANGHNANI | 2024-05-22 | 2024-05-24 | 2024-05-25 | 2024-06-06 | 2024-06-13 | 2024-06-20 | 32 |  |  | Approved
2 | 1317_ES-28-004089_RT_MOSTOLES VIOLETA 13-15_4089 | RAJ SANGHNANI | 24-05-2024 | 2024-05-27 | 2024-05-28 | 2024-06-06 | 2024-06-13 | 2024-06-20 | 40
3 | 1320_ES-28-032156_RT_MADRID MARCENADO ATW_32156 | ABHIYUKTHA | 24-05-2024 | 2024-05-27 | 29.05.2024 | 2024-06-06 | 2024-06-13 | 2024-06-20 | 32
4 | 1321_ES-28-032202_RT_MADRID AVDA DE AMERICA 17 ATW_32202 | ABHIYUKTHA | 2024-05-28 | 2024-05-30 | 2024-06-01 | 2024-06-06 | 2024-06-13 | 2024-06-20 | 40
5 | 1322_ES-28-032213_RT_MADRID ROSA SILVA ATW_32213 | RAJ SANGHNANI | 2024-05-29 | 2024-05-31 | 2024-06-01 | 2024-06-06 | 2024-06-13 | 2024-06-20 | 32
6 | 1876_ES-28-069259_RT_MADRID VALVERDE 25 ATW_69263 | RAJ SANGHNANI | 2024-06-07 | 2024-06-10 | 12-06.2024 | 12-06.2024 | 2024-06-29 | 2024-07-04 | 32
7 | 1877_ES-03-087216_RT_POLOP ATW_87680 | ALLSON | 2024-06-10 | 2024-06-12 | 2024-06-12 | 12-06.2024 | 2024-06-29 | 2024-07-04 | 24
8 | 1878_ES-03-087586_RT_ALTEA VILLA GADEA ATW_88050 | RAJ SANGHNANI | 2024-06-10 | 2024-06-12 | 2024-06-12 | 12-06.2024 | 2024-06-29 | 2024-07-04 | 24
9 | 1888_ES-03-031642_RT_VILLAJOYOSA AVDA JUAN CARLOS I 2 ATW_31642 | ROSHITH | 2024-06-10 | 2024-06-12 | 2024-06-12 | 12-06.2024 | 2024-06-29 | 2024-07-04 | 24
10 | 1889_ES-28-032189_RT_MADRID SAN LEOPOLDO 72 ATW_32189 | ABHIYUKTHA | 2024-06-10 | 2024-06-12 | 2024-06-12 | 12-06.2024 | 2024-06-29 | 2024-07-04 | 24
11 | 1916_ES-03-042476_RT_ELCHE CORAZON ATW_42476 | ALLSON | 2024-06-14 | 2024-06-16 | 2024-06-19 | 2024-06-27 | 2024-07-03 | 2024-07-16 | 40
12 | 1917_ES_03-055765_RT_COX ATW_55765 | RAJ SANGHNANI | 2024-06-14 | 2024-06-16 | 2024-06-20 | 2024-06-27 | 2024-07-03 | 2024-07-16 | 40
13 | 1926_ES-28-043479_RT_MADRID MARIA GUZMAN ATW_43479 | ROSHITH | 2024-06-14 | 2024-06-16 | 2024-06-20 | 2024-06-27 | 2024-07-04 | 2024-07-16 | 40
14 | 1929_ES-11-088386_RT_LINEA DE LA CONSEPTION SANTANDER 1 ATW_88850 | ABHIYUKTHA | 2024-06-14 | 2024-06-16 | 2024-06-20 | 2024-06-27 | 2024-07-03 | 2024-07-16 | 40
15 | 1930_ES-28-032183_RT_MADRID SAN FRANCISCO DE SALES 36 ATW_32183 | ALLSON | 2024-06-19 | 2024-06-21 | 2024-06-21 | 2024-06-27 | 2024-07-04 | 2024-07-16 | 24
16 | 1974_ES-35-063686_RT_GRAN CANARIA INGENIO CT ATW_63686 | RAJ SANGHNANI | 2024-06-28 | 2024-07-01 | 2024-07-01 | 2024-07-20 | NO COMMENTS |  | 24
17 | 1992_ES-33-063650_RT_UJO CT ATW_63650 | ABHIYUKTHA | 2024-06-26 | 2024-06-28 | 2024-07-20 | 2024-07-20 | NO COMMENTS |  | 24
18 | 1993_ES-35-063690_RT_GRAN CANARIA EL RISCO CT ATW_63690 | ALLSON | 2024-06-27 | 2024-06-29 | 2024-06-29 | 2024-06-29 | NO COMMENTS |  | 24
19 | 1994_ES-11-088301_RT_ALGECIRAS FRANCIA 5 ATW_88765 | ROSHITH | 2024-06-28 | 2024-07-01 | 2024-07-20 | 2024-07-20 | NO COMMENTS |  | 24
20 | 1995_ES-11-088334_RT_ALGECIRAS TENIENTE MIRANDA 77 ATW_88798 | ALLSON | 2024-07-01 | 2024-07-03 | 2024-07-20 | 2024-07-20 | NO COMMENTS |  | 24
21 | 2013_ES-11-087360_RT_SANLUCAR DE BARRAMEDA PZA HUELVA ATW_87824 | PRIYANKA | 2024-07-06 | 2024-07-10 | 2024-07-22 | 2024-07-31 | NO COMMENTS
22 | 2014_ES-03-088223_RT_ALFAS DEL PI CV-753 ATW_88687 | IBRAHIM | 2024-07-24 | 2024-07-26 | 2024-07-30 | 2024-07-31 | NO COMMENTS
23 | 2016_ES-46-002154_RT_GANDIA BENASUAI 5_2154 | AKSHAY | 2024-07-23 | 2024-07-25 | 2024-07-30 | 2024-07-31 | NO COMMENTS
24 | 2023_ES-36-063732_RT_DOMAIO PUEBLO CT ATW_63732 | PRIYANKA | 2024-07-23 | 2024-07-25 | 2024-07-30 | 2024-07-31 | NO COMMENTS
25 | 2026_ES-03-087329_RT_SAN ISIDRO ATW_87793 | TUSHAR | 2024-07-25 | 2024-07-29 | 2024-07-30 | 2024-07-31 | NO COMMENTS
26 | 2027_ES-03-087768_RT_ALBATERA ATW_88232 | JAYDEV | 2024-07-16 | 2024-07-19 | 2024-07-22 | 2024-08-09
27 | 2028_ES-03087820_RTCALPE LUXEMBERGO 1 ATW_88284 | AKSHAY | 2024-07-16 | 2024-07-19 | 2024-07-22 | 2024-08-09
28 | 2030_ES-39-091693_RT_POTES SAN ROQUE 4 ATW_92165 | PRIYANKA | 2024-07-31 | 2024-07-03 | 2024-08-06 | 2024-08-09
29 | 2037_ES-46-032819_RTVALENCIALITERATO AZORIN 47 ATW_32819 | RAJ SANGHNANI | 2024-07-31 | 2024-07-03 | 2024-08-06 | 2024-08-09
30 | 2038_ES-48-032887_RT_GETXO CAMPO DE GOLF ATW_32887 | PRIYANKA | 2024-08-05 | 2024-08-07 | 2024-08-09 | 2024-08-09
31 | 2043_ES-32-042187_RT_VERIN ATW_42187 | IBRAHIM | 2024-06-14: 2024-07-31; 2024-06-16: 2024-07-03; 2024-06-20: 2024-08-05
32 | 2044_ES-03-042428_RT_ASPE PUBELO ATW_42428 | TUSHAR | 2024-06-14: 2024-07-01; 2024-06-16: 2024-08-04; 2024-06-20: 2024-08-06
33 | 2045_ES-03-045456_RT_DOLORES SAN ISIDRO ATW_42456 | IBRAHIM
34 | 2046_ES-03-042509_RT_SALINAS AV GAURINOS ATW_42509 | TUSHAR
35 | 2047_ES-0-042536_RT_VILLAJOYOSACAV PAIS VALENCIANO ATW_42536 | PRIYANKA | 2024-06-14: 2024-08-09
36 | 1380_ES-28-069235_RT_MADRID SERRANO 195 ATW_69239
37 | 1388_ES-41-087654_RT_ARAHAL MALAGA ATW_88118
38 | 1406_ES-11-031942_RT_ROTA CHARCO 21 ATW_31942
39 | 1407_ES-28-032141_RT_TRES CANTOS AVDA LABRADORES 1 ATW_32141
40 | 1408_ES-41-032660_RT_SEVILLA EDIF FORUM AVDA LUIS MORALES 32 ATW_32660
41 | 1421_ES-43-045871_RT_TARRAGONA SANT PERE I SANT PAU ATW_45871
42 | 1452_ES-36-032564_RT_VIGO PIZARRO 65 ATW_32564
43 | 1457_ES-11-042103_RT_SANLUCAR DE BARRAMEDA ATW_42103
44 | 1458_ES-36-042274_RT_VIGO SOL ATW_42274
45 | 1459_ES-33-042638_RT_GIJON DOCTOR HURLE ATW_42638
46 | 1462_ES-23-043140_RT_JAEN OESTE ATW_43140
47 | 1464_ES-24-043213_RT_LEON ORDOÑO ATW_43213
48 | 1465_ES-24-043217_RT_VALVERDE LA VIRGEN HOTEL VILLAPALOMA ATW_43217
49 | 1466_ES-12-046318_RT_CASTELLON JOVER ATW_46318
50 | 1467_ES-41-082722_RT_PUEBLA DEL RIO AVDA VEGA 26 ATW_82921
51
52
53
54
55
56
57
58
59
60
61
62
63
64
65
66
67
68
69
70
71
72
73
74
75
76
77
78
79
80
81
82
83
84
85
86
87
88
89
90
91
92
93
94
95
96
97
98
99
100